## TimeLine
General Assembly Planning Timeline
Berkeley Apr. 30 - May 1, 2011
Action | Days Before/ |  | Action / Responsibility
Date | After GA |  | GAP | CC | SC/WG | IT | Other | Description | Completed
2010-12-31 | G – | 120 |  | X |  |  |  | Date, Host committee and venue decided.
|  |  |  | X |  |  |  | GA Planning Committee members recruited
|  |  | X | X |  | X |  | Date and location of GA sent to Contacts and Cocos lists, posted on web.
(Announcement includes candidate recruitment for any elections.)
2011-01-05 | G – | 115 | X |  |  |  |  | GA planning timeline created. Post on web. Notify CC and Cocos.
2011-02-04 | G – | 85 |  | X |  |  |  | Determine which counties are active.
to | to | [6 empty] | (Determined by CC Reg Reps and reported to State Liaison.)
2011-03-06 | G – | 55 |  |  |  |  | Liaison | Allocate 100 delegates to active counties and sends to GAP.
2011-02-14 | G – | 75 |  |  | X |  |  | Notify GAP of proposals that will be submitted.
(Proposals must be prepared using the proposal template.)
2011-02-24 | G – | 65 | X |  |  |  |  | GA schedule draft submitted to CC and Cocos.
2011-03-01 | G – | 60 |  |  | X |  |  | Submit proposals to GAP.
2011-03-06 | G – | 55 |  | X |  |  |  | CC approves schedule for agenda packet.
2011-03-16 | G – | 45 | X |  |  |  |  | Submit proposal agenda packet to IT.
|  |  | X | X |  |  |  | Prepare announcement for Contacts list.
[6 empty] | X |  | Post agenda packet on web; send announcement.
2011-03-24 | G – | 37 |  |  |  |  | Host | Provide necessary registration information to IT for registration page.
2011-03-31 | G – | 30 | X |  |  |  |  | Submit logistics agenda packet to IT.
[6 empty] | X |  | Post agenda packet on web; open registration page; send announcement on Contacts list.
2011-04-09 | G – | 21 | X | X |  |  |  | Recruit members for accreditation and election committees.
2011-04-23 | G – | 7 | X | X |  |  |  | Accreditation and election committees prepares all needed materials.
2011-04-27 | G – | 3 |  |  |  | X |  | Online registration and delegate submission closes,
IT sends registration data to host; delegate list to accred comm.
2011-04-29 | G – | 1 |  | X |  |  |  | Approve final draft agenda for submission to GA.
2011-04-30 |  | 0 |  |  |  |  | GA | Approve agenda.
2011-05-10 | G + | 10 | X |  |  |  |  | Notetaker submits Post-Plenary draft to GAP.
2011-05-14 | G + | 14 | X |  |  | X |  | Send Post-Plenary report to IT for Contacts list.
[5 empty] | X |  |  | Committees submit list of new members and cocos to CC.
[5 empty] | X |  |  | Submit to GAP final version of proposals approved by GA, including modifications and amendments.
2011-05-28 | G + | 28 | X |  |  |  |  | Notetaker submits final GA minutes to GAP.
|  |  | X |  |  | X |  | Send minutes to IT for posting. Send notice to CC and Cocos for internal review of minutes.
2011-06-04 | G + | 35 | X |  |  |  |  | GAP submits final draft minutes to IT for posting.
|  |  |  | X |  | X |  | CC prepares notice for Contacts and Coco lists; sends to IT.
|  | KEY: | CC = coordinating committee
GAP = general assembly planning (committee)
IT = information technology (group)
SC/WG = standing committees / working groups
Liaison = Liaison to the Secretary of State
Resources:
|  |  | GA Web Page |  |  | www.cagreens.org/plenary
|  |  | GAP email |  |  | agenda-team@cagreens.org
|  |  | Preparation Tools |  |  | www.cagreens.org/gap
|  |  | Proposal Template |  |  | www.cagreens.org/plenary/process.html